## DISCLAIMER
This worksheet is an example only, and does not take into account individual project assumptions or needs. Please seek professional assistance and advice to tailor this spreadsheet to your project and to assist with your decision making process.

## Profit and Loss
Project
Project Profit and Loss Statement
For the Period 01/07/17 - 31/12/18
Income
Interest |  |  | 19941.9723
Rebates |  |  | 0
Rent Received |  |  | 16500
Sales Revenue |  |  | 5350000
GST on Income |  |  | -386363.6364
5000078.3359
Land Aquistion and Development Costs
Acquisition Costs |  | 1162500
Design and Planning Costs |  | 88830
Contributions and Charges |  | 82250
Constructions Costs |  | 2056500
Development Management Fees |  | 176550
Project Management/Supervision |  | 0
Legals - Land Acquisition and Development |  | 9900
Total Land Aquistion and Development Costs |  |  | 3576530
Project and Entity Costs
Entity Costs |  | 59710
Finance Costs |  | 140054.8377
Sales and Marketing Costs |  | 338250
Holding Costs |  | 23426.272
Legals - Project and Entity |  | 22750
Total Project and Entity Costs |  |  | 584191.1097
GST on Costs |  |  | -259452.0155
Total Expenses |  |  | 3901269.0942
Net Profit after Interest |  |  | 1098809.2417
Financial Analysis
Gross Profit Margin | 28.47%
Net Profit Margin | 21.98%
Cost to Sales Ratio | 78.02%
Peak Debt | 2487754.8377
GRV Lend Ratio | 50.12%
LVR Land | 34.1%
LVR Construction hard Costs | 103.6%
Investor Analysis
Total Equity | 1100000
Equity Interest Return | 264000
Equity Profit Return | 393404.6208
Return on Equity | 59.76% | 27.58% | p.a
Developer Analysis
Total Equity | 200000
Equity Interest Return | 48000
Equity Profit Return | 393404.6208
Return on Equity | 220.7% | 101.9% | p.a
Development Management Fees | 176550

## Project Cashflow
Project
CASHFLOW PROJECTIONS AND FUND REQUIREMENTS
For the Period 01/07/17 - 31/12/18
Opening Cash | 0 | 1151013.75 | 1141324.1953 | 398939.4541 | 388908.6669 | 369756.7653 | 341074.898 | 338198.6651 | 323253.7828 | 262844.8344 | 224059.9665 | 160319.2289 | 106545.63 | 72324.7068 | 44749.329 | 38291.501 | 49569.6411 | 39941.6418 | 60399.4501 | 48568.4116 | 104538.7449 | 94694.5298 | 112857.019 | 98586.4648 | 45696.2788 | 2767472.0105 | 788217.1227
| July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | Total
Inflows
Bond refunds | [27 empty] | 0
Equity - Developer | July: 200000 | 200000
Equity - Investors | July: 1100000 | 1100000
Interest Received |  | 2397.9453 | 2377.7587 | 831.1239 | 810.2264 | 770.3266 | 710.5727 | 704.5806 | 673.4454 | 547.5934 | 466.7916 | 333.9984 | 221.9701 | 150.6765 | 93.2278 | 79.774 | 103.2701 | 83.2118 | 125.8322 | 101.1842 | 217.7891 | 197.2803 | 235.1188 | 205.3885 | 95.2006 | 5765.5667 | 1642.119 | 19941.9723
Loan Drawdown - Development | July: 102000; August: 595; September: 204598.4708; October: 1791.9619; November: 307802.415; December: 3597.9291; January: 717618.917; February: 7805.0274; March: 415850.5567; April: 10276.3516; May: 316336.297; June: 12181.5921; July: 12252.6514; August: 0 | 2112707.1701
Loan Drawdown - Land |  |  | 330000 | 1925 | 1936.2292 | 1947.5238 | 1958.8844 | 1970.3112 | 1981.8047 | 1993.3652 | 2004.9932 | 2016.689 | 2028.453 | 2040.2856 | 2052.1873 | 2064.1584 | 2076.1993 | 2088.3105 | 2100.4923 | 2112.7452 | 2125.0695 | 2137.4658 | 2149.9343 | 2162.4756 | 2175.09 |  |  | 375047.6676
Rebates | [27 empty] | 0
Rent Received | October: 1833.3333; November: 1833.3333; December: 1833.3333; January: 1833.3333; February: 1833.3333; March: 1833.3333; April: 1833.3333; May: 1833.3333; June: 1833.3333 | 16500
Sales Revenue | July: 5350000 | 5350000
GST Refund | 0 | 4448.75 | 1498.75 | 1230.5682 | 1260.4167 | 2090.4167 | 3005.8712 | 760.4167 | 760.4167 | 5760.4167 | 4260.4167 | 6385.4167 | 5637.6894 | 12888.0682 | 3740.6564 | 19507.1102 | 912.6059 | 28944.0163 | 1077.7425 | 66417.3889 | 1462.437 | 38823.8729 | 1688.4134 | 30224.3493 | 2312.6274 | 14273.1818 | 80 | 259452.0155
Total Inflows | 1300000 | 6846.6953 | 333876.5087 | 5820.0254 | 5840.2056 | 6641.6004 | 7508.6616 | 5268.6418 | 5249.0001 | 10134.7086 | 8565.5348 | 10569.4374 | 109888.1125 | 15674.0303 | 210484.5424 | 23443.0045 | 310894.4904 | 34713.4676 | 720922.984 | 76436.3456 | 419655.8523 | 51434.9705 | 320409.7635 | 44773.8054 | 5366835.5694 | 20038.7485 | 1722.119 | 9433648.8254
Outflows
Acquisition Costs
Deposit On Property | July: 100000 | 100000
Balance of Purchase Price | September: 1000000 | 1000000
Stamp Duty | September: 60500 | 60500
Settlement Adjustments | September: 2000 | 2000
Design and Planning Costs
3D Renders for Planning | December: 2750 | 2750
Archaeological Assessment | [27 empty] | 0
Architect | November: 5500; December: 5500; May: 5500 | 16500
Civil Engineer | December: 2200 | 2200
Contamination report | [27 empty] | 0
Draftsman | May: 27500 | 27500
Electrical Engineer | [27 empty] | 0
Energy Efficiency Ratings | December: 2100 | 2100
Environment and Sustainability Development | [27 empty] | 0
Fauna and Flora Assessment | [27 empty] | 0
Fire Consultant | [27 empty] | 0
Geotechnical/Soil Test | November: 880 | 880
Hydraulic Engineer | [27 empty] | 0
Interior Deisng Consultant | [27 empty] | 0
Land Scaping Design | December: 2750 | 2750
Land Surveyor | November: 2750; May: 5500 | 8250
Mechanical Engineer | [27 empty] | 0
Structural engineer | December: 2750 | 2750
Town Plan Application/Permit Fees | December: 1150 | 1150
Town Planning consultant | October: 5500; November: 5500; December: 5500; March: 5500 | 22000
Traffic Engineer | [27 empty] | 0
VCAT Allowance | [27 empty] | 0
Contributions and Charges
Application Fees | June: 1000 | 1000
Councill Open Space Contribution | June: 68750 | 68750
Electricity Sub Station | [27 empty] | 0
Fire Service Levy | [27 empty] | 0
Gas,Power,Water,Phone,Intern, connection fees | April: 12500 | 12500
Sewer Contribution Fees | [27 empty] | 0
Water Contribution Fees | [27 empty] | 0
Bonds - Refundable | [27 empty] | 0
Holding Costs
Council Rates | February: 2204.136; February: 2204.136 | 4408.272
General Maintnance | July: 0; August: 0; September: 0; October: 128.3333; November: 128.3333; December: 128.3333; January: 128.3333; February: 128.3333; March: 128.3333; April: 128.3333; May: 128.3333; June: 128.3333 | 1155
Insurances | July: 2750; July: 2750; July: 2750 | 8250
Land Tax | February: 7613 | 7613
Repairs /Replacement | [27 empty] | 0
Water Rates | September: 250; December: 250; March: 250; June: 250; September: 250; December: 250; March: 250; June: 250 | 2000
Entity Costs
Accounting Fees | 5500 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 2750 | 550 | 550 | 2750 | 24200
Administration Costs | [27 empty] | 0
ASIC Filing Fees | July: 250; July: 250 | 500
Bank Charges | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 1350
Book Keeping Costs | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 330 | 8910
Development Management Fees | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 | 7356.25 |  |  |  | 176550
Feasibility costs and Investor Document Preparation | July: 22000 | 22000
Formation, Entity Setup Costs | July: 2750 | 2750
Legal Fees
Borrowing documents | August: 2750; June: 2750 | 5500
Building Contract | June: 3850 | 3850
Consultant contracts | [27 empty] | 0
Contract & Vendor Statment | April: 2750 | 2750
Investors Agreements | July: 8250 | 8250
Lodgment Plan Sub | June: 2750 | 2750
Purchase Contract | September: 3300 | 3300
S173 Agreement | [27 empty] | 0
Settlment Legals | July: 6250 | 6250
Constructions Costs
Building Construction Costs | July: 102000; September: 204000; November: 306000; January: 714000; March: 408000; May: 306000 | 2040000
Demolition Costs | March: 16500 | 16500
Project Management/Supervision | [27 empty] | 0
Security Costs | [27 empty] | 0
Finance Costs
Brokerage Fees | August: 5500; June: 10200 | 15700
Interest Payable - Land Loan |  |  | 1925 | 1936.2292 | 1947.5238 | 1958.8844 | 1970.3112 | 1981.8047 | 1993.3652 | 2004.9932 | 2016.689 | 2028.453 | 2040.2856 | 2052.1873 | 2064.1584 | 2076.1993 | 2088.3105 | 2100.4923 | 2112.7452 | 2125.0695 | 2137.4658 | 2149.9343 | 2162.4756 | 2175.09 |  |  |  | 45047.6676
Interest Payable - Development Loan | July: 595; August: 598.4708; September: 1791.9619; October: 1802.415; November: 3597.9291; December: 3618.917; January: 7805.0274; February: 7850.5567; March: 10276.3516; April: 10336.297; May: 12181.5921; June: 12252.6514 | 72707.1701
Loan Repayments - Land Loan | July: 375047.6676 | 375047.6676
Loan Repayments - Development Loan | July: 2112707.1701 | 2112707.1701
QS Fees | September: 550; November: 550; January: 550; March: 550; May: 550 | 2750
Valuation Fee | June: 3850 | 3850
Sales and Marketing Costs
3 D Renders | March: 2750 | 2750
Advertising | March: 2750; April: 2750; May: 2750; June: 2750; July: 2750 | 13750
Commissions - Presales | April: 33000; May: 26125; June: 30250; July: 25437.5; August: 32312.5; July: 147125 | 294250
Commissions - Retail | [27 empty] | 0
Display Unit Works | [27 empty] | 0
Marketing Material | March: 16500 | 16500
Other Marketing | [27 empty] | 0
Printing Material | [27 empty] | 0
Signage & Boards | March: 2750 | 2750
Temp.fence & Electrical | March: 2750 | 2750
Travel,Accom,& Expens. | [27 empty] | 0
Web Site | March: 5500 | 5500
Equity & Profit Distributions
Equity Interest - Investors | August: 264000 | 264000
Equity Interest - Developer | August: 48000 | 48000
Equity Return - Investor | August: 1100000 | 1100000
Equity Return - Developer | August: 200000 | 200000
Profit Distribution - Investor | September: 393404.6208 | 393404.6208
Profit Distribution - Developer | September: 393404.6208 | 393404.6208
GST Payable | August: 386363.6364 | 386363.6364
Total Outflows | 148986.25 | 16536.25 | 1076261.25 | 15850.8125 | 24992.1072 | 35323.4677 | 10384.8946 | 20213.524 | 65657.9486 | 48919.5765 | 72306.2723 | 64343.0363 | 144109.0356 | 43249.4081 | 216942.3703 | 12164.8644 | 320522.4896 | 14255.6593 | 732754.0226 | 20466.0122 | 429500.0674 | 33272.4813 | 334680.3177 | 97663.9914 | 2645059.8377 | 1999293.6364 | 789939.2417 | 9433648.8254
Closing Cash | 1151013.75 | 1141324.1953 | 398939.4541 | 388908.6669 | 369756.7653 | 341074.898 | 338198.6651 | 323253.7828 | 262844.8344 | 224059.9665 | 160319.2289 | 106545.63 | 72324.7068 | 44749.329 | 38291.501 | 49569.6411 | 39941.6418 | 60399.4501 | 48568.4116 | 104538.7449 | 94694.5298 | 112857.019 | 98586.4648 | 45696.2788 | 2767472.0105 | 788217.1227 | 0 | 0

## Equity Allocation
Project
Allocation of Equity Raised
Application of Funds | Land
Acquisition Costs
Deposit On Property | 100000
Balance of Purchase Price | 670000
Stamp Duty | 60500
Settlement Adjustments | 2000
Design and Planning Costs
3D Renders for Planning | 2750
Archaeological Assessment | 0
Architect | 16500
Civil Engineer | 2200
Contamination report | 0
Draftsman | 27500
Electrical Engineer | 0
Energy Efficiency Ratings | 2100
Environment and Sustainability Development | 0
Fauna and Flora Assessment | 0
Fire Consultant | 0
Geotechnical/Soil Test | 880
Hydraulic Engineer | 0
Interior Deisng Consultant | 0
Land Scaping Design | 2750
Land Surveyor | 2750
Mechanical Engineer | 0
Structural engineer | 2750
Town Plan Application/Permit Fees | 1150
Town Planning consultant | 22000
Traffic Engineer | 0
VCAT Allowance | 0
Contributions and Charges
Application Fees | 0
Councill Open Space Contribution | 0
Electricity Sub Station | 0
Fire Service Levy | 0
Gas,Power,Water,Phone,Intern, connection fees | 0
Sewer Contribution Fees | 0
Water Contribution Fees | 0
Bonds - Refundable | 0
Holding Costs
Council Rates | 2204.136
General Maintnance | 1155
Insurances | 2750
Land Tax | 7613
Repairs /Replacement | 0
Water Rates | 1000
Entity Costs
Accounting Fees | 11550
Administration Costs | 0
ASIC Filing Fees | 0
Bank Charges | 600
Book Keeping Costs | 3960
Development Management Fees | 88275
Feasibility costs and Investor Document Preparation | 22000
Formation, Entity Setup Costs | 2750
Legal Fees
Borrowing documents | 5500
Building Contract | 3850
Consultant contracts | 0
Contract & Vendor Statment | 2750
Investors Agreements | 8250
Lodgment Plan Sub | 0
Purchase Contract | 3300
S173 Agreement | 0
Settlment Legals | 0
Constructions Costs
Building Construction Costs | 0
Demolition Costs | 16500
Project Management/Supervision | 0
Security Costs | 0
Finance Costs
Brokerage Fees | 15700
Interest Payable - Land Loan | 2028.453
Interest Payable - Development Loan | 0
Loan Repayments - Land Loan | 0
Loan Repayments - Development Loan | 0
QS Fees | 0
Valuation Fee | 3850
Sales and Marketing Costs
3 D Renders | 2750
Advertising | 11000
Commissions - Presales | 89375
Commissions - Retail | 0
Display Unit Works | 0
Marketing Material | 16500
Other Marketing | 0
Printing Material | 0
Signage & Boards | 2750
Temp.fence & Electrical | 2750
Travel,Accom,& Expens. | 0
Web Site | 5500
Cashflow Reserve | 47959.411
Total Equity Raised | 1300000

## Sales Schedule
Project
Sales Schedule
Apart. | No.Of | No of | Car | Internal | Deck/Porch | Total | Land | Sales | Sale Rate | Allotment | Land Value | GST Payable
Lot No. | Bedrm | Bathrm | Space | Size M2 | Size M2 | M2 | M2 | Valuation | Per M2 | Entitlment | Allocation | Estimate
1 | 4 | 3 | 2 | 270 | 30 | 300 | 300 | 1200000 | 4444.4444 | 22.06% | 243088.2353 | 86991.9786
2 | 3 | 2 | 2 | 215 | 30 | 245 | 250 | 950000 | 4418.6047 | 18.01% | 198522.0588 | 68316.1765
3 | 4 | 2 | 2 | 240 | 30 | 270 | 215 | 1100000 | 4583.3333 | 19.85% | 218779.4118 | 80110.9626
4 | 3 | 2 | 2 | 215 | 30 | 245 | 250 | 925000 | 4302.3256 | 18.01% | 198522.0588 | 66043.4492
5 | 4 | 3 | 2 | 270 | 30 | 300 | 300 | 1175000 | 4351.8519 | 22.06% | 243088.2353 | 84719.2513
|  |  | 10 | 1210 | 150 | 1360 |  | 5350000 | 4420.112 | 100% | 1102000 | 386181.8182

## Variance Analysis
Project
Sales and Costs Variance Analysis
Sales Variance (Allowing 6.6% Sales Costs)
| +20% | +15% | +10% | +5% | +0% | -5% | -10% | -15% | -20%
Sales ($) | 6420000 | 6152500 | 5885000 | 5617500 | 5350000 | 5082500 | 4815000 | 4547500 | 4280000
Profit Estimate | 2098189.2417 | 1848344.2417 | 1598499.2417 | 1348654.2417 | 1098809.2417 | 848964.2417 | 599119.2417 | 349274.2417 | 99429.2417
Costs Variance (Excl Entity, Sales and Marketing, Land Acquisition Costs)
| +20% | +15% | +10% | +5% | +0% | -5% | -10% | -15% | -20%
Costs ($) | 2808970.9131 | 2691930.4583 | 2574890.0036 | 2457849.5489 | 2340809.0942 | 2223768.6395 | 2106728.1848 | 1989687.7301 | 1872647.2754
Profit Estimate | 630647.4228 | 747687.8776 | 864728.3323 | 981768.787 | 1098809.2417 | 1215849.6964 | 1332890.1511 | 1449930.6058 | 1566971.0605

## Assumptions
Project
Assumptions